## Slide 1
NUS AIDF × MUFG · AI PRACTITIONER CERTIFICATE
M04 — The AI-Native Development Lifecycle
Delivery plan — facilitator, roamer, mentor
5 tables · 150 minutes · two human gates
Notes: WHAT THIS DECK IS
Your delivery plan, not teaching material. Nothing here goes on the
projector in front of participants -- the projector shows your TERMINAL
and the /about page. This deck is what you read beforehand and glance at
between stages.
The depth is in these notes. The slides are thin on purpose.
BEFORE THE ROOM FILLS -- three things that are yours alone:
1. Two windows. Terminal on the projector, this deck on your laptop.
2. /about open in a tab on the reference deployment. That is your opener
and it means you recite nothing from memory.
3. Your own Codespace already warm -- dependencies installed, `claude`
running. A cold start at 0:10 in front of a room is four dead minutes.
AND: tell the roamer and the mentor the one rule (slide 3) OUT LOUD before
anyone sits down. A well-meaning mentor who answers "what should we set
MIN_SCORE to?" with a number has just cut the spine out of stage 02.

## Slide 2
WHO DOES WHAT
The three of you
Manraj — front of room, projector
Builds the product side by side with the tables. Owns the clock. Is the release manager at both gates.
Roamer — moving, constantly
Never sits. Reads screens over shoulders. Catches the table that is stuck and has not said so.
Mentor — floating, senior
Takes the question the roamer cannot answer in thirty seconds. Holds the front when Manraj is at a table.
Notes: THE ROAMER'S JOB IS NOT TO HELP. IT IS TO NOTICE.
Say this to them directly. A table that is stuck and knows it will raise a
hand -- that table is fine. The table that costs you the room is the one
confidently building the wrong thing at 1:10, and the ONLY way to find it
is to read their screen at 0:50.
So the roamer reads screens. Constantly. They are looking for a gap between
what a table thinks it is doing and what is on the monitor.
THE MENTOR IS YOUR CLOCK INSURANCE.
There are two moments you physically cannot be at the front: gate 1 (0:25,
you are at five tables) and gate 2 (2:15, same). The mentor holds the room
and, critically, CALLS TIME ON YOU. Give them explicit permission now:
"At 0:43, call it, wherever I am. Stage 03 cannot be short."
Without that, gate 1 eats the build, and the build is where they learn to
drive the agent.
ONE KEYBOARD PER TABLE. The roamer enforces this in the first five minutes.
Five laptops open at one table produces five half-builds and no review.

## Slide 3
THE ONE RULE
Demonstrate the move. Never project the answer.
The moment your ten decisions are on the screen, five tables copy them — and the module is over.
Defending a decision you did not make is the thing M04 assesses.
Your D0–D9 stay on your laptop. Off the projector. Out of your mouth.
Notes: THIS IS THE SLIDE THAT MATTERS MOST. If you remember one thing from this
deck, it is this one.
You are building the same product, at the front, at the same time as they
build it. That is the right call -- a room that has never seen stage 01 done
once will spend twelve of its fifteen minutes working out what a stage IS.
But side-by-side has one failure mode, and it is fatal: they stop deciding
and start copying. PRD section 10 leaves ten decisions deliberately open
(embedding model, chunking, threshold, how many passages, what to do with
superseded policy, what to do when two policies conflict, and so on). Those
ten decisions ARE the assessment. At 2:15 you ask "why this threshold?" and
"the agent chose it" is a failed answer -- so is "you said 0.35".
SO THE RHYTHM FOR EVERY STAGE IS THREE BEATS:
1. You do the move on the projector. Two to three minutes. "Watch this."
2. They do it with THEIR content. Ten-plus minutes. You go quiet, the
roamer works the floor.
3. You show what it produced -- and SAY IT SHOULD NOT MATCH THEIRS.
That third beat is the one people skip, and it is the one that stops the
room hunting for the right answer. Say out loud: "mine looks like this.
Yours won't, and that's correct."
WHEN THEY PUSH -- and they will, around 0:30:
"I'm not going to tell you, and at 2:15 you'll be glad I didn't."

## Slide 4
0:00 · OPEN · 10 MIN
/about on the projector
Where we are · 2 min — M01 model, M02 tooling, M03 you shipped. Today it survives a review.
What we're building · 2 min — scroll the eight features.
The six stages · 3 min — stop on both gates. “I am that human.”
What done means · 2 min — read PRD §12 off the screen.
Go · 1 min — START-HERE.md, then pipeline/01-shape.md.
Notes: OPEN THE /about PAGE ON THE REFERENCE DEPLOYMENT. Do not present from
memory -- the page exists so you don't have to.
RECAP ONLY M03. Not M01 and M02 in any detail. One line each, then move.
The room was there; what they need is the handoff into today.
SCROLL SLOWLY THROUGH THE SIX STAGES AND STOP ON BOTH GATES.
"Twice today, a human says yes or no. I am that human." Point at yourself.
They should know before they start that approval is coming.
READ THE DEFINITION OF DONE OFF THE SCREEN, verbatim -- PRD section 12:
"Build the whole product, F1 to F8, and release it in one pull request.
But you are done when you have completed all six stages and deployed
that increment to your own URL. Not when the product is
feature-complete. CUT SCOPE, NEVER A STAGE."
That is the sentence the entire day hangs off. You will say it again at
1:15 and again at 2:20.
THE LINE THAT SETS UP THE WHOLE SESSION -- land this one:
"Your agent is going to be faster than you all morning. Twice, it is
going to be faster than you in the WRONG DIRECTION. Those two moments
are the module."
WATCH FOR: nobody opens START-HERE.md. Say the filename twice. Have the
roamer confirm all five screens are on it by 0:12.

## Slide 5
0:10 · STAGE 01 · SHAPE · 15 MIN
They write the criteria. Not the agent.
Project ~3 min: the agent's five-line summary, then it asks to be corrected.
Then stop sharing. They have twelve minutes.
“At 2:15 I'll ask you to read these to me. You cannot read back something you never wrote.”
Notes: ON THE PROJECTOR, ~3 MINUTES:
Paste your shape prompt, let the agent produce its five-line summary of
what it thinks you're building, then say:
"Look what it did. It told me what it thinks we're building and asked
me to correct it -- BEFORE writing a line. That is the whole stage.
You are not getting requirements from the agent. You are giving them
to it, in your words, so that later you can say whether they were met."
CHECK THE SUMMARY MENTIONS REFUSAL. If the agent's summary doesn't mention
that the product declines when the corpus can't support an answer, say so
out loud -- that's a finding, and the build will drift toward a chatbot
that never says no.
THEN STOP SHARING AND GO QUIET. Twelve minutes.
ROAMER -- three screens to read, and what each means:
* Agent wrote the criteria, team said "yes, looks good"
-> the stage failed silently. Ask only: "Whose words are those?"
* Criteria that cannot fail -- "the system is reliable"
-> untestable. Ask: "Show me the test that proves that."
* The table is ARGUING about what "refuses" means
-> this is the stage working. Walk away. Do not help.
MENTOR takes "how precise should the criteria be?" The answer:
precise enough that two people would agree on pass or fail WITHOUT
talking to each other.
RUNNING LATE? A table still arguing at 0:24 is doing the right thing in
the wrong slot: "Lock what you have. You can amend a ticket; you cannot
un-ship a build."

## Slide 6
0:25 · STAGE 02 · PLAN · 20 MIN · ⚠ THE FIRST GATE
The most important twenty minutes of the day
Project ~3 min: ten decisions, options, trade-offs — and it stops.
Then close your laptop lid. Physically. Visibly.
Walk the tables. ~90 seconds each. Three questions.
Reject one, if one deserves it. All five passing first time teaches that the gate is theatre.
Notes: EVERYTHING BEFORE THIS IS SET-UP. EVERYTHING AFTER IS EXECUTION.
ON THE PROJECTOR, ~3 MIN: paste the decision-interview prompt. The agent
lists ten decisions with options and trade-offs AND STOPS.
"Ten decisions. It gave me options and trade-offs and then it waited.
It did not pick. If yours picks for you -- that is a finding, write it
down, it is the most interesting thing you will see today."
THEN CLOSE YOUR LAPTOP LID. Do it visibly. It is the clearest possible
signal that your answers are not coming. You will be asked anyway.
FOR THE TABLE THAT SAYS "YOU DECIDE" -- this reframing works every time:
"Then tell me what you'd REGRET. If you set the threshold too low it
answers questions it shouldn't. Too high and it refuses things it
knows. Which of those two would you rather explain to the bank?"
They are not choosing a number. They are choosing which failure they can
live with -- and that, they can do.
THE GATE. Walk to each table, ~90 seconds, and SAY the time limit out loud
so they feel it. Mentor holds the clock at the front.
1. "Why this chunk size?" -> a reason about THEIR corpus, not a default
2. "Why this threshold?" -> that they know what it costs them
3. "What are you NOT doing?" -> an actual answer. "Nothing" is a failed plan
REJECT ONE IF ONE DESERVES IT. A room where all five pass at first ask
learns that the gate is theatre. "Come back in three minutes with a reason
for D2" costs three minutes and teaches the entire session.
MENTOR: at 0:43, CALL IT, wherever Manraj is. Stage 03 cannot be short.

## Slide 7
0:45 · STAGE 03 · BUILD · 60 MIN
You stop presenting. You start walking.
0:55 Roamer confirms all five tables have F1 running. No ingestion = will not finish F5.
1:15 The mid-point call. Front of room, loud, thirty seconds.
1:30 Quiet walk. Note which feature each table is on — this is your 2:15 script.
1:40 “Five minutes. Commit what works. Broken code does not go into a review.”
Notes: THE LONG ONE. Your job changes completely: you stop presenting.
START YOUR BUILD, LET ONE TEST GO GREEN ON SCREEN, then:
"Red, then green, then commit. I'm going to leave my screen up but I'm
not going to talk about it. Come and look if you want to see where
I am."
LEAVE YOUR TERMINAL PROJECTED ALL HOUR. A table that is lost finds it far
easier to glance at a screen than to raise a hand.
THE 1:15 MID-POINT CALL -- say this close to verbatim, then SHUT UP FOR A
FULL TEN SECONDS and let them actually decide:
"Half the build is gone. Decide now, as a table, where you're stopping.
F6, F7 and F8 are cuttable and I mean that -- a table that ships F1 to
F5 clean and tells me what they cut has the better run today. The one
thing I will not accept is a product built by skipping the review.
CUT SCOPE, NEVER A STAGE. Say your number out loud to each other now."
ROAMER -- the four failures, in the order they appear:
* Agent added a dependency without asking -> "Did you approve that?"
It is an explicit stage-03 rule.
* Tests weakened to go green -> STOP THEM. This is the one that cannot
pass. Everything else is recoverable; this isn't.
* Nobody has run the app 45 minutes in -> "Open localhost:3000. Now."
* Watching the agent type, nobody reading -> "What's it building right
now?" No answer means that table is a passenger.
IF A CODESPACE DIES -- roamer handles it, Manraj does not leave the front:
1. ./scripts/start.sh -- fixes most things
2. 502 on *.app.github.dev -> USE THE EDITOR PREVIEW. That is the fix,
not a workaround. curl says 200 the whole time, so it reads as a
broken build and is not.
3. Still dead -> new Codespace from table-N, ~3 min. Work is committed.

## Slide 8
1:45 · STAGE 04 · REVIEW · 20 MIN
One character. No failing test.
Run pass 1 on the planted defect live. It finds > 75 where the policy says “£75 or more”.
Every claim at exactly £75 goes through without approval. The code reads fine.
“One pass finds the crash. The fifth finds this.”
Notes: THIS IS YOUR BEST THREE MINUTES OF THE DAY. Do not rush it, and do not
pre-empt the answer -- let the agent find it live on the screen.
Run review pass 1 (CORRECTNESS ONLY) on docs/review-example/expense_rules.py
against the travel policy section 4.2. It finds `if claim.amount_gbp > 75:`
where the policy says "£75 or more".
"One character. Every claim at exactly seventy-five pounds goes through
without approval, and no test fails, and the code reads fine. This is
what five passes are for. One pass finds the crash. The fifth finds
this."
Answers and grading are in docs/instructor/review-example-answers.md if a
table wants to go deeper.
THEN SET THEM OFF ON THEIR OWN DIFF:
"Same five passes on your own code. ONE PASS PER MESSAGE -- if you ask
for all five at once you get five shallow ones. Every finding gets a
decision written down, INCLUDING the ones you're not fixing. 'We know
and we accepted it' is a professional answer. 'We didn't look' is not."
ROAMER: teams finding nothing in their own code are not reviewing -- they
are asking the agent whether its own work is good. Ask: "Which pass are you
on, and what did it say?"
THE HONEST RISK HERE: tables arrive at 1:45 mid-feature and want to keep
building. HOLD THE LINE. This stage is learning outcome M04.4 and it is
what the certificate is actually about. A table that skips it has not done
the module, however good their product looks.

## Slide 9
2:05 · STAGE 05 · RELEASE · 10 MIN · ⚠ THE SECOND GATE
Three hours in, and none of it has been near a URL
One PR carrying the whole product. Four checks run. Nothing deploys.
“The merge is the deploy, and the merge needs a human.”
Write the rollback before you merge. Writing it afterwards is called an incident report.
They cannot approve their own PR. That is the control, not GitHub being awkward.
Notes: ON THE PROJECTOR, ~2 MIN -- write the release plan, then push and open the
PR on screen:
gh pr create --base table-3 --head work/table-3 \
--title "T1: the policy assistant" --fill
"Four checks run. NOTHING DEPLOYS. Three hours in and none of this has
been near a URL. The merge is the deploy, and the merge needs a human."
THIS IS WHERE THE DEPLOYMENT LESSON LANDS, so don't skate over it. No table
ever runs a deploy command. Railway watches refs/heads/table-N; merging the
PR is what puts software in front of users. The point: RELEASE IS A
GOVERNANCE ACT, NOT A COMMAND. A table that could type `railway up` would
never feel that.
ON THE ROLLBACK -- the line that lands:
"Write the rollback BEFORE you merge. Not because you'll need it.
Because writing it afterwards is called an incident report."
BRANCH PROTECTION WILL BITE ONE TABLE. They cannot approve their own pull
request. Say so as a control, not an apology:
"A different person approves. That's not GitHub being awkward, that's
the control. Find someone at another table."
That cross-table approval is also the best thirty seconds of peer learning
in the session -- someone from table 2 reading table 4's diff.

## Slide 10
2:15 · STAGE 06 · VERIFY · 15 MIN · YOU ARE THE RELEASE MANAGER
Six questions, table by table
1 Show me your ticket. 2 Read me your criteria — in your words.
3 Show me the test that was red and is now green.
4 Which review finding did you accept, and why?
5 How do we get this back if it is wrong?
6 What did you cut, and does the interface still offer it?
Notes: ~2 MINUTES PER TABLE. ASK ALL SIX EVEN WHEN YOU CAN SEE THE ANSWER -- the
room is watching the ritual, not the result.
All six answered -> approve -> merge -> about 90 seconds -> live.
*** THEN WAIT TWO MINUTES BEFORE READING /healthz ***
A freshly deployed container indexes the corpus in a background thread so
the health endpoint can answer while it works. For the first minute or two
the vector store says "collection not created yet", then flips to
"135 passages indexed". IT IS A COLD START, NOT A FAILED BUILD. Refresh
before you send anyone back to their agent. (Seen for real on table-3.)
Question 6 exists because of the one-PR scope. Cutting F7 is completely
legitimate. A top bar still advertising "Corpus" after they cut it is the
product claiming something that isn't there -- and this is the last moment
to catch it.
WHEN A TABLE SHOWS YOU A REFUSAL, say this:
"Watch what it just did. It had a model that would happily have answered
that, and it refused BEFORE it even called it. That's not the product
failing. That's the only reason a bank would let it near a staff
member."
AND SAY THIS OUT LOUD, IN FRONT OF EVERYONE -- name the table:
"Table 4 cut two features and shipped something that works, with a
review record and a rollback. THAT is the better run today. If you
remember one thing from this module, make it that one."
If you don't say it, the next cohort hears that eight features was the bar.
CLOSING QUESTION, TO EVERY TABLE:
"Where did AI help, where did it displace or risk something, and which
control caught it?"

## Slide 11
IF YOU ARE BEHIND
Cut in this order
1 Your own projector build after stage 03 — costs nothing; they have the pattern by then.
2 Gate 1 to three tables, mentor takes two — costs consistency, not substance.
3 Stage 06 down to one question: “which finding did you accept?”
4 F6–F8 room-wide at 1:15 — the demo looks thinner. Nothing else changes.
Nothing above touches the review or the two gates.
Notes: THE ORDER MATTERS. Work down it, and do not jump.
NOTHING IN THIS LIST TOUCHES THE REVIEW OR THE TWO GATES. Those are the
module. Features are not.
IF YOU ARE SO FAR BEHIND THAT THE GATES ARE IN QUESTION: run stage 06 for
TWO tables in front of the whole room and let the other three watch.
Three tables seeing a real gate beats five tables having a rushed one.
That is a genuinely acceptable outcome and you should feel fine about it.
The failure mode you are avoiding is five tables each getting ninety
seconds of a gate that nobody believed in.
WHAT YOU DO NOT DO, UNDER ANY TIME PRESSURE:
* Fix a table's scope-check failure for them. Send them back to revert.
The failure IS the lesson.
* Give a table your D0-D9 to save them five minutes in stage 02.
* Let a table skip the review to finish a feature.

## Slide 12
AFTERWARDS
Record while it is fresh
Which feature each table reached — this sets the real F-target for cohort 2.
Did any agent decide D0–D9 without being asked to? Verbatim.
Did any table try to skip the review to finish a feature?
The best answer to the closing question.
Then: ./scripts/reset_table.sh N for all five.
Notes: DO THIS IN THE TEN MINUTES AFTER THE ROOM EMPTIES, not that evening.
THE FIRST LINE IS THE IMPORTANT ONE. Which feature each table actually
reached is the only honest basis for the next cohort's timings and for the
1:15 mid-point prompt. If every table stopped at F5, then F5 is the real
target and the deck should say so next time.
THE SECOND IS THE MOST VALUABLE FINDING YOU CAN BRING BACK. If an agent
skipped the decision interview and picked the ten decisions itself, capture
the exact wording -- that is a scaffold defect, and it is fixable in the
stage file before the next run.
RESETTING: ./scripts/reset_table.sh N takes about twenty seconds per table
and puts the branch back to main. Do all five. A table branch left carrying
the previous cohort's build is the single most confusing thing a new table
can open.